## C_BG_01
Bug ID : | C_BG_01
Bug Name : | Absence of "Captcha" functionality
Bug Description : | Captcha Functionality for Security Purpose
Steps to Reproduce : | 1. Open browser 2. Enter url 3. check login page 4. Check Captcha
Test Case ID : | C_TS01_TC16
Bug Assigned to : | Vishvjeet Singh Chavhan
Developer Email : | vish123@gmail.com
Status : | new
Severity Of Bug : | Low
Priority Of Bug : | Major
ScreenShot :

## C_BG_02
Bug ID : | C_BG_02
Bug Name : | CDAC ACTS Logo Failed to Navigate
Bug Description : | When User Click On CDAC ACTS Logo it Give yoy 404 Page Not Found
Steps to Reproduce : | 1. Go to Google 2. Enter the Web http://ccst-testvm.pune.cdac.in:8080/epAdmin/index.jsp 3. Click On CDAC ACTS Logo
Test Case ID : | C_TS01_TC17
Bug Assigned to : | Vivek Tiwari
Developer Email : | Vivek123@gmail.com
Status : | New
Severity Of Bug : | Medium
Priority Of Bug : | Medium
ScreenShot :

## C_BG_03
Bug ID : | C_BG_03
Bug Name : | ReadMore Navigate to Wrong Page
Bug Description : | When User Click on Login Page readmore option it Will Navigate to the CDAC ACTS Home Page
Steps to Reproduce : | 1. Go to Google 2. Enter the Web http://ccst-testvm.pune.cdac.in:8080/epAdmin/index.jsp 3. Click On readmore Anchor Tag
Test Case ID : | C_TS01_TC18
Bug Assigned to : | Vivek Tiwari
Developer Email : | vivek123@gmail.com
Status : | New
Severity Of Bug : | Low
Priority Of Bug : | Low
ScreenShot :

## C_BG_04
Bug ID : | C_BG_04
Bug Name : | Back Navigation Arrow Not Working
Bug Description : | When User Click on Back Navigation Button buut you will stilll on same page
Steps to Reproduce : | 1. Goo to Google 2. Enter the Web http://ccst-testvm.pune.cdac.in:8080/epAdmin/index.jsp 3. Login With Valid Credentials 4.Click on Modules and Questions 5. CC Click on Back Navigation Arrow
Test Case ID : | C_TS03_TC07
Bug Assigned to : | manoj Ambhore
Developer Email : | manoj123@gmail.com
Status : | New
Severity Of Bug : | Medium
Priority Of Bug : | Major
ScreenShot :

## C_BG_05
Bug ID : | C_BG_05
Bug Name : | Exam Date Schedule after Course End
Bug Description : | When CC trying to Schedule Exam After Course End
Steps to Reproduce : | 1. Select Module 2. Select date after course end 3. Enter Questions=20, Duration=60, Passing=10 4. Click Schedule 5. Verify exam must not be scheduled
Test Case ID : | C_TS09_TC08
Bug Assigned to : | Vishvjeet Singh Chauhan
Developer Email : | vish123@gmail.com
Status : | New
Severity Of Bug : | Critical
Priority Of Bug : | Critical
ScreenShot :

## C_BG_06
Bug ID : | C_BG_06
Bug Name : | Duration Of Exam
Bug Description : | When CC trying to Scheduling Exam , It Accept Any time for exam
Steps to Reproduce : | 1. Enter Duration = 1000 minutes 2. Click Schedule 3. Verify system blocks with max limit validation
Test Case ID : | C_TS09_TC22
Bug Assigned to : | Vivek Tiwari
Developer Email : | vivek123@gmail.com
Status : | New
Severity Of Bug : | critical
Priority Of Bug : | medium
ScreenShot :

## C_BG_07
Bug ID : | C_BG_07
Bug Name : | Accept Zero as Passing Crtiria
Bug Description : | When CC trying to Scheduling Exam It Accept Zero as Passing Mark Criteria
Steps to Reproduce : | 1. Enter Passing Marks = 0 2. Click Schedule 3. Verify exam not scheduled
Test Case ID : | C_TS09_TC30
Bug Assigned to : | Manoj Ambhore
Developer Email : | manoj123@gmail.com
Status : | New
Severity Of Bug : | Critical
Priority Of Bug : | Critical
ScreenShot :

## C_BG_08
Bug ID : | C_BG_08
Bug Name : | Session Invalidated After Password Change
Bug Description : | When CC Change the Password it Will Stilll on Same Page
Steps to Reproduce : | 1. Try accessing application without re-login 2. Verify session is invalidated
Test Case ID : | C_TS11_TC18
Bug Assigned to : | Vishvjeet Singh Chauhan
Developer Email : | vish123@gmail.com
Status : | New
Severity Of Bug : | Critical
Priority Of Bug : | Critical
ScreenShot :

## C_BG_09
Bug ID : | C_BG_09
Bug Name : | CC Display Admis Home Page Details
Bug Description : | When CC Login and trying to to enter Admins home page web in address area
Steps to Reproduce : | 1. click on Forget password functionality
Test Case ID : | C_TS02_TC14
Bug Assigned to : | Vivek Tiwari
Developer Email : | viivek123@gmail.com
Status : | New
Severity Of Bug : | Critical
Priority Of Bug : | High
ScreenShot :

## C_BG_10
Bug ID : | C_BG_10
Bug Name : | Update the Exam Question Paper on Exam day
Bug Description : | CC login , click on exam modules and questions then click on repo , then display the alert
Steps to Reproduce : | 1. login 2. click on modules and qestions 3.click on repo questions
Test Case ID : | C_TS03_TC10
Bug Assigned to : | Vishvjeet Singh Chauhan
Developer Email : | vish123@gmail.com
Status : | New
Severity Of Bug : | Critical
Priority Of Bug : | High
ScreenShot :

## C_BG_11
Bug ID : | C_BG_11
Bug Name : | when cc trying to update the ppassword to default for selected student
Bug Description : | when cc trying to update the ppassword to default for selected student
Steps to Reproduce : | 1. login 2. click on managed student 3.click on edit student 4. select the som student 5.click on deafult
Test Case ID : | C_TS12_TC25
Bug Assigned to : | Vishvjeet Singh Chauhan
Developer Email : | vish123@gmail.com
Status : | New
Severity Of Bug : | medium
Priority Of Bug : | High
ScreenShot :